## Task List
BBH Integration — Infrastructure Setup Task List
SEI × BBH ¦ Strangler Fig Migration ¦ OpenShift + Airflow + dbt + Oracle + Apigee
Phase | Task ID | Task Name | Owner | Priority | Est. Days | Dependencies | Status | Assigned To | Notes
Phase 1 — Pre-Setup & Coordination
Phase 1 — Pre-Setup & Coordination | 1.1.1 | Identify task owners across all teams | Shared | Critical | 1 |  | Not Started |  | Data Eng, Cloud Eng, DBA, Network, BBH, Apigee
Phase 1 — Pre-Setup & Coordination | 1.1.2 | Schedule kickoff with all stakeholders | Shared | Critical | 1 | 1.1.1 | Not Started |  | Include BBH team and program manager
Phase 1 — Pre-Setup & Coordination | 1.1.3 | Confirm environment promotion strategy (dev→QA→UAT→prod) | Data Engineering | Critical | 1 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.1.4 | Agree on change management process for prod | Shared | High | 1 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.2.1 | Confirm BBH file format specification | BBH Team | Critical | 2 | 1.1.2 | Not Started |  | SEI CSV fields, Advantage output format, naming conventions, SLA
Phase 1 — Pre-Setup & Coordination | 1.2.2 | Confirm SEI API details (URLs, auth, rate limits, endpoints) | Data Engineering | Critical | 2 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.2.3 | Confirm Oracle DB details (host, port, SID per env) | DBA Team | Critical | 1 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.2.4 | Confirm Apigee details and PingIdentity IDP endpoints | Apigee / Integration | High | 1 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.2.5 | Document all confirmed details in Confluence / wiki | Data Engineering | High | 2 | 1.2.1,1.2.2,1.2.3,1.2.4 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.3.1 | Request OpenShift cluster admin access for team | Data Engineering | Critical | 1 | 1.1.1 | Not Started |  | Submit via cloud engineering ticket
Phase 1 — Pre-Setup & Coordination | 1.3.2 | Request Oracle DBA team to create service accounts | DBA Team | Critical | 2 | 1.2.3 | Not Started |  | airflow_rw, dbt_runner, consumer_advantage, consumer_swp
Phase 1 — Pre-Setup & Coordination | 1.3.3 | Request firewall rules — pods → Oracle DB | Network / Security | Critical | 3 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.3.4 | Request firewall rules — pods → SEI API | Network / Security | Critical | 3 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.3.5 | Request firewall rules — pods → Apigee, SFTP, BBH | Network / Security | Critical | 3 | 1.1.2 | Not Started
Phase 1 — Pre-Setup & Coordination | 1.3.6 | Request SSL certificates for all routes | Network / Security | Critical | 5 | 1.1.2 | Not Started |  | airflow.bbh.sei.internal, dbt-docs.bbh.sei.internal (prod/uat/qa/dev)
Phase 1 — Pre-Setup & Coordination | 1.3.7 | Request PingIdentity OAuth2 client registration per env | Network / Security | High | 3 | 1.2.4 | Not Started |  | One client per env, scopes: accounts:read, positions:read
Phase 1 — Pre-Setup & Coordination | 1.3.8 | Request Apigee API product access credentials | Apigee / Integration | High | 2 | 1.2.4 | Not Started
Phase 2 — OpenShift Project Setup
Phase 2 — OpenShift Project Setup | 2.1.1 | Create OpenShift project: bbh-prod | Data Engineering | Critical | 1 | 1.3.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.1.2 | Create OpenShift project: bbh-uat | Data Engineering | Critical | 1 | 1.3.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.1.3 | Create OpenShift project: bbh-qa | Data Engineering | Critical | 1 | 1.3.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.1.4 | Create OpenShift project: bbh-dev | Data Engineering | Critical | 1 | 1.3.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.1.5 | Configure resource quotas per project (prod higher limits) | Data Engineering | High | 1 | 2.1.1,2.1.2,2.1.3,2.1.4 | Not Started
Phase 2 — OpenShift Project Setup | 2.1.6 | Configure LimitRange per project | Data Engineering | High | 1 | 2.1.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.1.7 | Request cloud engineering to label new node for BBH workloads | Cloud Engineering | Critical | 1 | 1.1.2 | Not Started |  | Node affinity rules required
Phase 2 — OpenShift Project Setup | 2.2.1 | Create service accounts: airflow-webserver-sa per project | Data Engineering | Critical | 1 | 2.1.1,2.1.4 | Not Started
Phase 2 — OpenShift Project Setup | 2.2.2 | Create service accounts: airflow-worker-sa per project | Data Engineering | Critical | 1 | 2.1.1,2.1.4 | Not Started
Phase 2 — OpenShift Project Setup | 2.2.3 | Create service accounts: dbt-runner-sa per project | Data Engineering | Critical | 1 | 2.1.1,2.1.4 | Not Started
Phase 2 — OpenShift Project Setup | 2.2.4 | Create service accounts: dbt-docs-sa, sftp-server-sa | Data Engineering | Medium | 1 | 2.1.1,2.1.4 | Not Started
Phase 2 — OpenShift Project Setup | 2.2.5 | Create RBAC roles: data-engineering-admin, pipeline-operator, bbh-viewer | Data Engineering | High | 1 | 2.2.1,2.2.2 | Not Started
Phase 2 — OpenShift Project Setup | 2.2.6 | Bind RBAC roles to team members per environment | Data Engineering | High | 1 | 2.2.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.3.1 | Create network policy: airflow webserver/worker → PostgreSQL | Data Engineering | Critical | 1 | 2.1.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.3.2 | Create network policy: airflow worker → Oracle DB (egress) | Data Engineering | Critical | 1 | 2.1.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.3.3 | Create network policy: airflow worker → SEI API (egress) | Data Engineering | Critical | 1 | 2.1.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.3.4 | Create network policy: airflow worker → SFTP, Apigee (egress) | Data Engineering | High | 1 | 2.1.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.3.5 | Create network policy: monitoring → all pods (scrape) | Data Engineering | Medium | 1 | 2.1.5 | Not Started
Phase 2 — OpenShift Project Setup | 2.4.1 | Identify available StorageClass on OpenShift cluster | Data Engineering | Critical | 1 | 2.1.1 | Not Started |  | Confirm with cloud engineering
Phase 2 — OpenShift Project Setup | 2.4.2 | Create PVC: PostgreSQL (prod 100GB, lower 20GB) | Data Engineering | Critical | 1 | 2.4.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.4.3 | Create PVC: Airflow DAGs (shared webserver + workers) | Data Engineering | Critical | 1 | 2.4.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.4.4 | Create PVC: Airflow logs, dbt docs, SFTP landing zone | Data Engineering | High | 1 | 2.4.1 | Not Started
Phase 2 — OpenShift Project Setup | 2.4.5 | Verify PVC binding on new node and test read/write | Data Engineering | Critical | 1 | 2.4.2,2.4.3,2.4.4 | Not Started
Phase 3 — Container Image Build
Phase 3 — Container Image Build | 3.1.1 | Confirm OpenShift internal image registry enabled | Cloud Engineering | Critical | 1 | 2.1.1 | Not Started
Phase 3 — Container Image Build | 3.1.2 | Configure image registry storage and access credentials | Data Engineering | Critical | 1 | 3.1.1 | Not Started
Phase 3 — Container Image Build | 3.1.3 | Define image tagging strategy per environment | Data Engineering | High | 1 | 3.1.2 | Not Started |  | sei/airflow-base:2.10.2, sei/dbt-oracle:1.7.5, etc.
Phase 3 — Container Image Build | 3.2.1 | Write Dockerfile: Airflow base (v2.10.2 + Oracle client) | Data Engineering | Critical | 2 | 3.1.3 | Not Started |  | Include cx_Oracle, pandas, requests, tenacity, slack_sdk
Phase 3 — Container Image Build | 3.2.2 | Build and push Airflow base image to registry | Data Engineering | Critical | 1 | 3.2.1 | Not Started
Phase 3 — Container Image Build | 3.2.3 | Test Airflow image runs in dev namespace | Data Engineering | Critical | 1 | 3.2.2 | Not Started
Phase 3 — Container Image Build | 3.2.4 | Vulnerability scan: Airflow image | Network / Security | High | 1 | 3.2.2 | Not Started
Phase 3 — Container Image Build | 3.3.1 | Write Dockerfile: dbt-oracle (Python 3.10.12 + dbt v1.7.5) | Data Engineering | Critical | 2 | 3.1.3 | Not Started |  | Include dbt-oracle adapter, Oracle Instant Client
Phase 3 — Container Image Build | 3.3.2 | Build and push dbt-oracle image to registry | Data Engineering | Critical | 1 | 3.3.1 | Not Started
Phase 3 — Container Image Build | 3.3.3 | Test dbt compile and dbt run against dev Oracle schema | Data Engineering | Critical | 2 | 3.3.2 | Not Started
Phase 3 — Container Image Build | 3.3.4 | Vulnerability scan: dbt-oracle image | Network / Security | High | 1 | 3.3.2 | Not Started
Phase 3 — Container Image Build | 3.4.1 | Write Dockerfile: BBH Custom Transformer | Data Engineering | Critical | 3 | 3.1.3 | Not Started |  | SEI CSV parsing, Advantage output, SFTP client (paramiko)
Phase 3 — Container Image Build | 3.4.2 | Build and push BBH Transformer image | Data Engineering | Critical | 1 | 3.4.1 | Not Started
Phase 3 — Container Image Build | 3.4.3 | Test transformer against sample SEI CSV — validate Advantage output | Data Engineering | Critical | 2 | 3.4.2 | Not Started
Phase 3 — Container Image Build | 3.5.1 | Write Dockerfile: nginx dbt docs server with basic auth | Data Engineering | Medium | 1 | 3.1.3 | Not Started
Phase 3 — Container Image Build | 3.5.2 | Build and push nginx dbt docs image | Data Engineering | Medium | 1 | 3.5.1 | Not Started
Phase 4 — Secret & Config Management
Phase 4 — Secret & Config Management | 4.1.1 | Create OpenShift Secrets: Oracle DB credentials per namespace | Data Engineering | Critical | 1 | 1.3.2 | Not Started |  | host, port, service name, username, password
Phase 4 — Secret & Config Management | 4.1.2 | Create OpenShift Secrets: PostgreSQL credentials per namespace | Data Engineering | Critical | 1 | 2.1.5 | Not Started
Phase 4 — Secret & Config Management | 4.1.3 | Create OpenShift Secrets: SEI API credentials per namespace | Data Engineering | Critical | 1 | 1.2.2 | Not Started |  | client_id, client_secret, token_url, base_url
Phase 4 — Secret & Config Management | 4.1.4 | Create OpenShift Secrets: PingIdentity OAuth credentials | Data Engineering | High | 1 | 1.3.7 | Not Started
Phase 4 — Secret & Config Management | 4.1.5 | Create OpenShift Secrets: BBH SFTP credentials | Data Engineering | High | 1 | 1.2.1 | Not Started |  | host, port, username, private_key
Phase 4 — Secret & Config Management | 4.1.6 | Create OpenShift Secrets: Airflow Fernet key, dbt docs htpasswd | Data Engineering | High | 1 | 2.1.5 | Not Started
Phase 4 — Secret & Config Management | 4.1.7 | Verify all secrets accessible from pods | Data Engineering | Critical | 1 | 4.1.1,4.1.6 | Not Started
Phase 4 — Secret & Config Management | 4.1.8 | Document secret rotation schedule | Data Engineering | High | 1 | 4.1.7 | Not Started
Phase 4 — Secret & Config Management | 4.2.1 | Create ConfigMaps: airflow.cfg per environment | Data Engineering | Critical | 1 | 2.1.5 | Not Started
Phase 4 — Secret & Config Management | 4.2.2 | Create ConfigMaps: dbt profiles per environment | Data Engineering | Critical | 1 | 2.1.5 | Not Started |  | Thread counts, target schemas
Phase 4 — Secret & Config Management | 4.2.3 | Create ConfigMaps: nginx dbt docs, Oracle TNS, feature flags | Data Engineering | High | 1 | 2.1.5 | Not Started
Phase 4 — Secret & Config Management | 4.2.4 | Create ConfigMaps: BBH field mapping configuration | Data Engineering | High | 2 | 1.2.1 | Not Started |  | SEI → Advantage field map
Phase 5 — PostgreSQL Deployment
Phase 5 — PostgreSQL Deployment | 5.1.1 | Deploy PostgreSQL 16 pod per namespace | Data Engineering | Critical | 1 | 4.1.2,2.4.2 | Not Started
Phase 5 — PostgreSQL Deployment | 5.1.2 | Configure PostgreSQL resource limits per environment | Data Engineering | High | 1 | 5.1.1 | Not Started |  | Prod: 2 CPU 4GB ¦ Lower: 1 CPU 2GB
Phase 5 — PostgreSQL Deployment | 5.1.3 | Create Airflow metadata database and user | Data Engineering | Critical | 1 | 5.1.1 | Not Started
Phase 5 — PostgreSQL Deployment | 5.1.4 | Create PostgreSQL ClusterIP Service per namespace | Data Engineering | Critical | 1 | 5.1.1 | Not Started
Phase 5 — PostgreSQL Deployment | 5.2.1 | Verify PostgreSQL persistent storage survives pod restart | Data Engineering | Critical | 1 | 5.1.1 | Not Started
Phase 5 — PostgreSQL Deployment | 5.2.2 | Run airflow db init — verify metadata tables created | Data Engineering | Critical | 1 | 5.1.3 | Not Started
Phase 5 — PostgreSQL Deployment | 5.2.3 | Set up PostgreSQL metrics export for Prometheus | Data Engineering | Medium | 1 | 5.1.1 | Not Started
Phase 6 — Airflow Deployment
Phase 6 — Airflow Deployment | 6.1.1 | Deploy Airflow scheduler pod per namespace | Data Engineering | Critical | 1 | 5.2.2,3.2.3 | Not Started
Phase 6 — Airflow Deployment | 6.1.2 | Mount DAGs PVC on scheduler pod | Data Engineering | Critical | 1 | 6.1.1,2.4.3 | Not Started
Phase 6 — Airflow Deployment | 6.1.3 | Configure scheduler resource limits (prod: 2 CPU 4GB) | Data Engineering | High | 1 | 6.1.1 | Not Started
Phase 6 — Airflow Deployment | 6.2.1 | Deploy Airflow webserver — prod: 2 replicas, lower: 1 | Data Engineering | Critical | 1 | 6.1.1 | Not Started
Phase 6 — Airflow Deployment | 6.2.2 | Configure liveness and readiness probes on webserver | Data Engineering | High | 1 | 6.2.1 | Not Started
Phase 6 — Airflow Deployment | 6.2.3 | Set up PodDisruptionBudget for prod (min 1 available) | Data Engineering | High | 1 | 6.2.1 | Not Started
Phase 6 — Airflow Deployment | 6.2.4 | Configure Airflow RBAC: Admin, Viewer, Op roles | Data Engineering | High | 1 | 6.2.1 | Not Started |  | Admin=data-eng, Viewer=BBH, Op=operators
Phase 6 — Airflow Deployment | 6.2.5 | Configure auth backend: PingIdentity OAuth2 (prod/uat) | Data Engineering | High | 2 | 1.3.7,6.2.1 | Not Started |  | Built-in auth for QA/dev
Phase 6 — Airflow Deployment | 6.3.1 | Deploy Airflow worker deployment per namespace | Data Engineering | Critical | 1 | 6.1.1 | Not Started
Phase 6 — Airflow Deployment | 6.3.2 | Configure HPA: prod min 3 max 9, UAT min 2 max 5, QA/dev 1-2 | Data Engineering | Critical | 1 | 6.3.1 | Not Started |  | HPA trigger: CPU > 70%, task queue depth
Phase 6 — Airflow Deployment | 6.3.3 | Set worker resource limits (prod: 4 CPU 8GB, lower: 2 CPU 4GB) | Data Engineering | High | 1 | 6.3.1 | Not Started
Phase 6 — Airflow Deployment | 6.3.4 | Configure Airflow Connections: Oracle, SEI API, SFTP, Slack | Data Engineering | Critical | 2 | 4.1.1,4.1.3,4.1.5 | Not Started
Phase 6 — Airflow Deployment | 6.3.5 | Test worker picks up and executes test DAG | Data Engineering | Critical | 1 | 6.3.1,6.3.4 | Not Started
Phase 6 — Airflow Deployment | 6.4.1 | Create OpenShift Service for Airflow webserver | Data Engineering | Critical | 1 | 6.2.1 | Not Started
Phase 6 — Airflow Deployment | 6.4.2 | Create OpenShift Route: airflow.bbh.sei.internal (prod) | Data Engineering | Critical | 1 | 6.4.1,1.3.6 | Not Started |  | TLS edge termination, HTTP→HTTPS redirect
Phase 6 — Airflow Deployment | 6.4.3 | Create OpenShift Routes for UAT, QA, dev environments | Data Engineering | High | 1 | 6.4.1,1.3.6 | Not Started
Phase 6 — Airflow Deployment | 6.4.4 | Test Airflow UI accessible from internal network via route | Data Engineering | Critical | 1 | 6.4.2,6.4.3 | Not Started
Phase 6 — Airflow Deployment | 6.4.5 | Share Airflow URL with BBH team and data engineering team | Data Engineering | High | 1 | 6.4.4 | Not Started
Phase 7 — Oracle Database Setup
Phase 7 — Oracle Database Setup | 7.1.1 | Raise DBA request: create schemas RAW_SWP, STG_SWP, INT_CANONICAL | DBA Team | Critical | 3 | 1.3.2 | Not Started
Phase 7 — Oracle Database Setup | 7.1.2 | Raise DBA request: create schemas MART_ADVANTAGE, MART_SWP, MART_OPS | DBA Team | Critical | 3 | 1.3.2 | Not Started
Phase 7 — Oracle Database Setup | 7.1.3 | Raise DBA request: create service accounts and grant permissions | DBA Team | Critical | 2 | 7.1.1,7.1.2 | Not Started |  | airflow_rw, dbt_runner, consumer_advantage, consumer_swp
Phase 7 — Oracle Database Setup | 7.2.1 | Create RAW_SWP tables: accounts, positions, transactions, securities | Data Engineering | Critical | 2 | 7.1.1 | Not Started |  | Partitioned by loaded_at / trade_date
Phase 7 — Oracle Database Setup | 7.2.2 | Create MART_OPS tables: dbt_mart_watermark, consumer_registry | Data Engineering | High | 1 | 7.1.2 | Not Started
Phase 7 — Oracle Database Setup | 7.2.3 | Create Oracle roles: ADVANTAGE_CONSUMER_ROLE, SWP_CONSUMER_ROLE | DBA Team | High | 1 | 7.1.3 | Not Started
Phase 7 — Oracle Database Setup | 7.2.4 | Grant roles to consumer service accounts | DBA Team | High | 1 | 7.2.3 | Not Started
Phase 7 — Oracle Database Setup | 7.3.1 | Configure Oracle Instant Client in worker pods | Data Engineering | Critical | 1 | 3.3.2,7.1.3 | Not Started
Phase 7 — Oracle Database Setup | 7.3.2 | Set up Oracle wallet / TNS configuration on OpenShift | Data Engineering | Critical | 1 | 7.3.1 | Not Started
Phase 7 — Oracle Database Setup | 7.3.3 | Test Oracle connectivity from worker pods per environment | Data Engineering | Critical | 1 | 7.3.2,1.3.3 | Not Started
Phase 7 — Oracle Database Setup | 7.3.4 | Validate bulk insert performance: target 10,000 rows/batch | Data Engineering | High | 1 | 7.3.3 | Not Started
Phase 8 — dbt Project Setup
Phase 8 — dbt Project Setup | 8.1.1 | Initialize dbt project repository with directory structure | Data Engineering | Critical | 1 | 3.3.3 | Not Started |  | models/staging, intermediate, marts/advantage, marts/swp
Phase 8 — dbt Project Setup | 8.1.2 | Configure dbt_project.yml: materialization, tags, schema names | Data Engineering | Critical | 1 | 8.1.1 | Not Started
Phase 8 — dbt Project Setup | 8.2.1 | Configure profiles.yml per environment (dev/qa/uat/prod) | Data Engineering | Critical | 1 | 8.1.1,4.2.2 | Not Started |  | Thread counts: dev 4, prod 8
Phase 8 — dbt Project Setup | 8.2.2 | Test dbt debug and dbt compile from worker pod | Data Engineering | Critical | 1 | 8.2.1 | Not Started
Phase 8 — dbt Project Setup | 8.3.1 | Build dbt staging models: stg_swp__accounts, positions, transactions, securities | Data Engineering | Critical | 3 | 7.2.1,8.2.2 | Not Started
Phase 8 — dbt Project Setup | 8.3.2 | Build dbt intermediate models: int_canonical__entities, holdings, trades | Data Engineering | Critical | 3 | 8.3.1 | Not Started
Phase 8 — dbt Project Setup | 8.3.3 | Build Advantage mart models: mart_adv__account_master, position_detail, trans_history | Data Engineering | Critical | 3 | 8.3.2 | Not Started |  | Exact Advantage field names
Phase 8 — dbt Project Setup | 8.3.4 | Build SWP mart models: mart_swp__accounts, holdings, activity | Data Engineering | Critical | 3 | 8.3.2 | Not Started |  | Modern naming + new fields
Phase 8 — dbt Project Setup | 8.3.5 | Build MART_OPS models: watermark, consumer_registry | Data Engineering | High | 1 | 8.3.3,8.3.4 | Not Started
Phase 8 — dbt Project Setup | 8.3.6 | Add dbt contracts to all mart models (enforced: true) | Data Engineering | Critical | 2 | 8.3.3,8.3.4 | Not Started |  | Prevents silent schema drift
Phase 8 — dbt Project Setup | 8.3.7 | Add dbt exposures for all consumers in exposures.yml | Data Engineering | High | 2 | 8.3.3,8.3.4 | Not Started |  | Migration status tracked here
Phase 8 — dbt Project Setup | 8.3.8 | Add dbt source freshness checks and dbt tests (not_null, unique, relationships) | Data Engineering | High | 2 | 8.3.1 | Not Started
Phase 8 — dbt Project Setup | 8.4.1 | Create dbt snapshots: snap_canonical__entities, snap_canonical__holdings | Data Engineering | Medium | 2 | 8.3.2 | Not Started |  | Phase 2 bi-temporal — start accumulating now
Phase 8 — dbt Project Setup | 8.4.2 | Test snapshot run in dev environment | Data Engineering | Medium | 1 | 8.4.1 | Not Started
Phase 9 — SFTP Server Setup
Phase 9 — SFTP Server Setup | 9.1.1 | Deploy SFTP server pod on OpenShift | Data Engineering | Critical | 1 | 2.4.4 | Not Started
Phase 9 — SFTP Server Setup | 9.1.2 | Configure SFTP directory structure: inbound, processed, failed, outbound | Data Engineering | Critical | 1 | 9.1.1 | Not Started
Phase 9 — SFTP Server Setup | 9.1.3 | Configure SFTP credentials from OpenShift Secret | Data Engineering | Critical | 1 | 9.1.1,4.1.5 | Not Started
Phase 9 — SFTP Server Setup | 9.1.4 | Create OpenShift Service and Route for SFTP | Data Engineering | Critical | 1 | 9.1.1 | Not Started
Phase 9 — SFTP Server Setup | 9.1.5 | Test SFTP connection from SEI Data Integrator | Data Engineering | Critical | 1 | 9.1.4 | Not Started
Phase 9 — SFTP Server Setup | 9.1.6 | Test SFTP connection from BBH system | BBH Team | Critical | 1 | 9.1.4 | Not Started
Phase 9 — SFTP Server Setup | 9.1.7 | Configure file retention policy (processed: 30d, failed: 90d) | Data Engineering | High | 1 | 9.1.2 | Not Started
Phase 9 — SFTP Server Setup | 9.2.1 | Create Airflow SFTP connection | Data Engineering | Critical | 1 | 6.3.4,9.1.3 | Not Started
Phase 9 — SFTP Server Setup | 9.2.2 | Build SFTPSensor DAG task (poke interval 60s) | Data Engineering | Critical | 2 | 9.2.1 | Not Started |  | Watch /inbound/sei/ for new files
Phase 9 — SFTP Server Setup | 9.2.3 | Build file move task (processed on success, failed on failure) | Data Engineering | High | 1 | 9.2.2 | Not Started
Phase 9 — SFTP Server Setup | 9.2.4 | Test end-to-end file trigger in dev | Data Engineering | Critical | 1 | 9.2.3 | Not Started
Phase 10 — Airflow DAG Development
Phase 10 — Airflow DAG Development | 10.1.1 | Build DAG: sei_api_extract (accounts, positions, transactions, securities) | Data Engineering | Critical | 3 | 6.3.5,7.3.3 | Not Started |  | Schedule: every 15 min prod
Phase 10 — Airflow DAG Development | 10.1.2 | Build DAG: dbt_staging_run (tag:staging, triggered after extract) | Data Engineering | Critical | 1 | 8.3.1,6.3.5 | Not Started
Phase 10 — Airflow DAG Development | 10.1.3 | Build DAG: dbt_intermediate_run (tag:intermediate) | Data Engineering | Critical | 1 | 8.3.2,10.1.2 | Not Started
Phase 10 — Airflow DAG Development | 10.1.4 | Build DAG: dbt_mart_run (Advantage + SWP in parallel) | Data Engineering | Critical | 1 | 8.3.3,8.3.4,10.1.3 | Not Started
Phase 10 — Airflow DAG Development | 10.1.5 | Build DAG: dbt_test_run (alert Slack on failure, block consumers) | Data Engineering | Critical | 1 | 10.1.4 | Not Started
Phase 10 — Airflow DAG Development | 10.1.6 | Build DAG: dbt_snapshot_run (daily, after staging) | Data Engineering | Medium | 1 | 8.4.2,10.1.2 | Not Started
Phase 10 — Airflow DAG Development | 10.2.1 | Build DAG: bbh_file_ingest (SFTP sensor, validate, load to RAW_SWP) | Data Engineering | Critical | 2 | 9.2.4,7.2.1 | Not Started
Phase 10 — Airflow DAG Development | 10.2.2 | Build DAG: bbh_transform (trigger BBH Transformer, validate row counts) | Data Engineering | Critical | 2 | 3.4.3,10.2.1 | Not Started
Phase 10 — Airflow DAG Development | 10.2.3 | Build DAG: bbh_file_deliver (outbound SFTP, notify BBH, watermark update) | Data Engineering | Critical | 2 | 10.2.2 | Not Started
Phase 10 — Airflow DAG Development | 10.3.1 | Build DAG: consumer_migration_check (query registry, flag zero-consumer models) | Data Engineering | High | 2 | 8.3.7,6.3.5 | Not Started |  | Weekly migration status report
Phase 10 — Airflow DAG Development | 10.3.2 | Build DAG: dbt_docs_refresh (generate after mart run, copy to PVC) | Data Engineering | High | 1 | 10.1.4 | Not Started
Phase 10 — Airflow DAG Development | 10.3.3 | Build DAG: oracle_health_check (ping, row count vs previous run, alert anomaly) | Data Engineering | High | 1 | 7.3.3 | Not Started
Phase 10 — Airflow DAG Development | 10.3.4 | Build DAG: sei_api_token_refresh (every 55 min, store in Airflow Variable) | Data Engineering | High | 1 | 6.3.4 | Not Started
Phase 11 — dbt Docs Publishing
Phase 11 — dbt Docs Publishing | 11.1.1 | Deploy nginx pod per namespace to serve dbt docs | Data Engineering | High | 1 | 3.5.2,2.4.4 | Not Started |  | Prod: 1 replica, lower: shared
Phase 11 — dbt Docs Publishing | 11.1.2 | Configure nginx ConfigMap: SPA routing, basic auth (prod/uat), no auth (dev) | Data Engineering | High | 1 | 11.1.1 | Not Started
Phase 11 — dbt Docs Publishing | 11.1.3 | Create OpenShift Service for nginx dbt docs | Data Engineering | High | 1 | 11.1.1 | Not Started
Phase 11 — dbt Docs Publishing | 11.1.4 | Create OpenShift Route: dbt-docs.bbh.sei.internal (prod) | Data Engineering | High | 1 | 11.1.3,1.3.6 | Not Started |  | TLS edge termination
Phase 11 — dbt Docs Publishing | 11.1.5 | Create OpenShift Routes: dbt-docs-uat, dbt-docs-dev | Data Engineering | Medium | 1 | 11.1.3 | Not Started
Phase 11 — dbt Docs Publishing | 11.1.6 | Test dbt docs accessible from browser via route | Data Engineering | High | 1 | 11.1.4,11.1.5 | Not Started
Phase 11 — dbt Docs Publishing | 11.2.1 | Create basic auth credentials (data-eng, BBH read-only, migration team) | Data Engineering | High | 1 | 11.1.2 | Not Started |  | Store htpasswd in OpenShift Secret
Phase 11 — dbt Docs Publishing | 11.2.2 | Test auth blocks unauthenticated access to prod/uat docs | Data Engineering | High | 1 | 11.2.1 | Not Started
Phase 11 — dbt Docs Publishing | 11.2.3 | Optional: Integrate dbt docs with PingIdentity SSO | Data Engineering | Low | 3 | 1.3.7 | Not Started
Phase 11 — dbt Docs Publishing | 11.3.1 | Add dbt docs generate step to Airflow DAG (after mart run) | Data Engineering | High | 1 | 10.3.2,11.1.1 | Not Started
Phase 11 — dbt Docs Publishing | 11.3.2 | Test full cycle: dbt run → docs generate → PVC copy → browser reflects update | Data Engineering | High | 1 | 11.3.1 | Not Started
Phase 11 — dbt Docs Publishing | 11.3.3 | Share dbt docs URLs with data engineering, BBH stakeholders, migration team | Data Engineering | High | 1 | 11.1.6 | Not Started
Phase 12 — Apigee Integration
Phase 12 — Apigee Integration | 12.1.1 | Create Apigee proxy: sei-integration-proxy | Apigee / Integration | Critical | 2 | 1.3.8 | Not Started
Phase 12 — Apigee Integration | 12.1.2 | Configure target endpoint → SEI API backend | Apigee / Integration | Critical | 1 | 12.1.1 | Not Started
Phase 12 — Apigee Integration | 12.1.3 | Deploy policy: OAuth-Verify-CRM (PingIdentity JWT) | Apigee / Integration | Critical | 1 | 12.1.1,1.3.7 | Not Started
Phase 12 — Apigee Integration | 12.1.4 | Deploy policies: KVM-Get-SEI-Token, SC-Refresh-SEI-Token | Apigee / Integration | Critical | 2 | 12.1.1 | Not Started |  | Token cache in Apigee KVM
Phase 12 — Apigee Integration | 12.1.5 | Deploy policies: JS-Translate-Request, JS-Translate-Response | Apigee / Integration | Critical | 2 | 12.1.1 | Not Started |  | Advantage ↔ SWP field translation
Phase 12 — Apigee Integration | 12.1.6 | Deploy policies: Quota-CRM-Limit (1000/min), Spike-Arrest (10/sec) | Apigee / Integration | High | 1 | 12.1.1 | Not Started
Phase 12 — Apigee Integration | 12.1.7 | Deploy policy: Response-Cache (5 min TTL) | Apigee / Integration | High | 1 | 12.1.1 | Not Started
Phase 12 — Apigee Integration | 12.1.8 | Test Apigee proxy end-to-end in test environment | Apigee / Integration | Critical | 2 | 12.1.3,12.1.5 | Not Started
Phase 12 — Apigee Integration | 12.1.9 | Deploy proxy to prod | Apigee / Integration | Critical | 1 | 12.1.8 | Not Started
Phase 12 — Apigee Integration | 12.2.1 | Register all integrations in Apigee API Hub | Apigee / Integration | High | 2 | 12.1.9 | Not Started |  | sei-accounts, sei-positions, sei-transactions, bbh-transformer
Phase 12 — Apigee Integration | 12.2.2 | Add OpenAPI specs for each product in API Hub | Apigee / Integration | High | 2 | 12.2.1 | Not Started
Phase 12 — Apigee Integration | 12.2.3 | Configure consumer metadata: mart_version, migration_status, deprecation_date | Apigee / Integration | High | 1 | 12.2.1 | Not Started
Phase 12 — Apigee Integration | 12.2.4 | Set up approval workflow (manual) and publish Integration Menu portal | Apigee / Integration | High | 2 | 12.2.1 | Not Started
Phase 12 — Apigee Integration | 12.3.1 | Create Apigee KVM: sei-credentials (client_id, secret, token_url) | Apigee / Integration | Critical | 1 | 12.1.1 | Not Started |  | Encrypted
Phase 12 — Apigee Integration | 12.3.2 | Create Apigee KVM: consumer-routing (consumer ID → mart version map) | Apigee / Integration | High | 1 | 12.1.1 | Not Started
Phase 13 — Monitoring & Alerting
Phase 13 — Monitoring & Alerting | 13.1.1 | Deploy Prometheus on OpenShift (or connect to existing) | Data Engineering | High | 2 | 2.1.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.1.2 | Configure Prometheus scrape targets: Airflow, PostgreSQL, nginx, node | Data Engineering | High | 1 | 13.1.1,6.2.1,5.1.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.1.3 | Configure Prometheus alerting rules: DAG failure, worker OOM, Oracle down, SFTP miss | Data Engineering | High | 2 | 13.1.2 | Not Started
Phase 13 — Monitoring & Alerting | 13.1.4 | Configure Prometheus alerting rules: mart row count anomaly, dbt test failure | Data Engineering | High | 1 | 13.1.2 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.1 | Deploy Grafana on OpenShift (or connect to existing) | Data Engineering | High | 1 | 13.1.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.2 | Build Grafana dashboard: Airflow DAG Health (success rate, duration, queue) | Data Engineering | High | 2 | 13.2.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.3 | Build Grafana dashboard: Pipeline Data Flow (row counts, model run times) | Data Engineering | High | 2 | 13.2.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.4 | Build Grafana dashboard: Infrastructure Health (CPU, memory, HPA, new node) | Data Engineering | High | 1 | 13.2.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.5 | Build Grafana dashboard: Consumer Migration Tracker (per mart, cohort progress) | Data Engineering | High | 2 | 13.2.1,8.3.7 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.6 | Build Grafana dashboard: BBH File Processing (received, transform rate, delivery latency) | Data Engineering | High | 2 | 13.2.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.2.7 | Configure Grafana auth (PingIdentity SSO) and create OpenShift route | Data Engineering | Medium | 1 | 13.2.1,1.3.7 | Not Started
Phase 13 — Monitoring & Alerting | 13.3.1 | Configure Slack alerting: create channels #bbh-pipeline-alerts, #bbh-pipeline-prod | Data Engineering | High | 1 | 6.3.4 | Not Started
Phase 13 — Monitoring & Alerting | 13.3.2 | Configure Airflow → Slack on DAG failure | Data Engineering | High | 1 | 13.3.1,6.3.4 | Not Started
Phase 13 — Monitoring & Alerting | 13.3.3 | Configure Prometheus → Slack webhook alerts | Data Engineering | High | 1 | 13.1.3,13.3.1 | Not Started
Phase 13 — Monitoring & Alerting | 13.3.4 | Configure PagerDuty for critical prod alerts: Oracle down, all workers OOM | Data Engineering | High | 1 | 13.1.3 | Not Started |  | Prod only
Phase 13 — Monitoring & Alerting | 13.3.5 | Configure email alerts to BBH team: file delivery confirmation, weekly migration report | Data Engineering | High | 1 | 13.3.1 | Not Started
Phase 14 — CI/CD Pipeline Setup
Phase 14 — CI/CD Pipeline Setup | 14.1.1 | Create Git repositories: sei-bbh-dbt, sei-bbh-airflow-dags, sei-bbh-infrastructure, sei-bbh-images | Data Engineering | Critical | 1 | 1.1.3 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.1.2 | Configure branch strategy: main→prod, uat→uat, develop→dev | Data Engineering | High | 1 | 14.1.1 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.1.3 | Set up branch protection rules and code review requirements | Data Engineering | High | 1 | 14.1.2 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.2.1 | Set up OpenShift Pipelines (Tekton) or Jenkins | Data Engineering | High | 2 | 2.1.5 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.2.2 | Configure CI triggers on PR: dbt compile, dbt test, Python lint, Docker build test | Data Engineering | High | 2 | 14.2.1,8.2.2 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.2.3 | Configure CI status checks as PR gate | Data Engineering | High | 1 | 14.2.2 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.3.1 | Configure CD triggers on merge: dev→deploy dev, uat→deploy uat | Data Engineering | High | 2 | 14.2.1 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.3.2 | Configure prod deployment: manual approval gate (data-eng lead + BBH team) | Data Engineering | Critical | 1 | 14.3.1 | Not Started
Phase 14 — CI/CD Pipeline Setup | 14.3.3 | Configure CD stages: build image, deploy manifests, sync DAGs, dbt compile, smoke test | Data Engineering | High | 2 | 14.3.1 | Not Started
Phase 15 — Testing & Validation
Phase 15 — Testing & Validation | 15.1.1 | Test Oracle connectivity from each namespace (dev/qa/uat/prod) | Data Engineering | Critical | 1 | 7.3.3 | Not Started
Phase 15 — Testing & Validation | 15.1.2 | Test SEI API call from Airflow worker pod | Data Engineering | Critical | 1 | 10.1.1 | Not Started
Phase 15 — Testing & Validation | 15.1.3 | Test SFTP file drop → Airflow sensor trigger | Data Engineering | Critical | 1 | 9.2.4 | Not Started
Phase 15 — Testing & Validation | 15.1.4 | Test dbt run end-to-end in dev schema | Data Engineering | Critical | 1 | 8.3.8 | Not Started
Phase 15 — Testing & Validation | 15.1.5 | Test dbt docs generation and browser serving | Data Engineering | High | 1 | 11.3.2 | Not Started
Phase 15 — Testing & Validation | 15.1.6 | Test Airflow webserver UI accessible via route | Data Engineering | Critical | 1 | 6.4.4 | Not Started
Phase 15 — Testing & Validation | 15.1.7 | Test HPA scales workers under load | Data Engineering | High | 1 | 6.3.2 | Not Started
Phase 15 — Testing & Validation | 15.1.8 | Test PostgreSQL survives pod restart (data persists) | Data Engineering | Critical | 1 | 5.2.1 | Not Started
Phase 15 — Testing & Validation | 15.1.9 | Test secret rotation does not break running pods | Data Engineering | High | 1 | 4.1.7 | Not Started
Phase 15 — Testing & Validation | 15.2.1 | Run full pipeline end-to-end in dev: SEI API → RAW_SWP → dbt stages → marts → watermark | Data Engineering | Critical | 2 | 10.1.5 | Not Started
Phase 15 — Testing & Validation | 15.2.2 | Run full BBH file pipeline in dev: SFTP arrival → ingest → transform → deliver → archive | Data Engineering | Critical | 2 | 10.2.3 | Not Started
Phase 15 — Testing & Validation | 15.2.3 | Validate Advantage mart output matches BBH Advantage format spec | Data Engineering | Critical | 2 | 15.2.1 | Not Started
Phase 15 — Testing & Validation | 15.2.4 | Validate SWP mart output matches expected schema | Data Engineering | Critical | 1 | 15.2.1 | Not Started
Phase 15 — Testing & Validation | 15.2.5 | Test Apigee proxy routes CRM call through to SEI API | Apigee / Integration | Critical | 1 | 12.1.8 | Not Started
Phase 15 — Testing & Validation | 15.2.6 | UAT sign-off with BBH team on file format and delivery | BBH Team | Critical | 3 | 15.2.2,15.2.3 | Not Started
Phase 15 — Testing & Validation | 15.2.7 | Performance test: full pipeline under prod-like load | Data Engineering | High | 2 | 15.2.1 | Not Started
Phase 15 — Testing & Validation | 15.2.8 | Prod go-live readiness checklist and sign-off | Shared | Critical | 1 | 15.2.6,15.2.7 | Not Started |  | All team leads must approve

## Summary Dashboard
BBH Integration — Program Manager Summary Dashboard
OpenShift + Airflow + dbt + Oracle + Apigee ¦ Strangler Fig Migration
Phase | Description | Primary Owner | Priority | Est. Days | Target Week | Status | Notes
Phase 1 | Pre-Setup & Coordination | Shared | Critical | 8 | Week 1 | Not Started
Phase 2 | OpenShift Project Setup | Data Engineering | Critical | 5 | Week 1-2 | Not Started
Phase 3 | Container Image Build | Data Engineering | Critical | 6 | Week 2-3 | Not Started
Phase 4 | Secret & Config Management | Data Engineering | Critical | 2 | Week 2 | Not Started
Phase 5 | PostgreSQL Deployment | Data Engineering | Critical | 2 | Week 3 | Not Started
Phase 6 | Airflow Deployment | Data Engineering | Critical | 5 | Week 3-4 | Not Started
Phase 7 | Oracle Database Setup | DBA Team | Critical | 5 | Week 2-3 | Not Started
Phase 8 | dbt Project Setup | Data Engineering | Critical | 10 | Week 3-5 | Not Started
Phase 9 | SFTP Server Setup | Data Engineering | Critical | 3 | Week 4 | Not Started
Phase 10 | Airflow DAG Development | Data Engineering | Critical | 8 | Week 4-6 | Not Started
Phase 11 | dbt Docs Publishing | Data Engineering | High | 4 | Week 5 | Not Started
Phase 12 | Apigee Integration | Apigee / Integration | Critical | 7 | Week 4-6 | Not Started
Phase 13 | Monitoring & Alerting | Data Engineering | High | 6 | Week 5-6 | Not Started
Phase 14 | CI/CD Pipeline Setup | Data Engineering | High | 5 | Week 5-6 | Not Started
Phase 15 | Testing & Validation | Shared | Critical | 10 | Week 6-8 | Not Started
TOTAL ESTIMATED DAYS |  |  |  | 86
TEAM OWNERSHIP LEGEND
Data Engineering
Cloud Engineering
DBA Team
Network / Security
BBH Team
Apigee / Integration
Shared

## Team Coordination
BBH Integration — Team Coordination & Dependency Map
Your Task | Depends On | Wait For Team | Blocking Your Task | Risk If Delayed | Mitigation
OpenShift namespace setup | Cluster admin access | Cloud Engineering | Everything else | Critical | Raise access ticket Day 1
Oracle schema creation | DBA service accounts | DBA Team | dbt models, Airflow DAGs | Critical | Raise DBA ticket Week 1
Firewall rules (Oracle) | Network team approval | Network / Security | Worker pod → Oracle connectivity | Critical | Raise ticket Week 1 — 3-5 day lead time
Firewall rules (SEI API) | Network team approval | Network / Security | sei_api_extract DAG | Critical | Raise ticket Week 1 — 3-5 day lead time
SSL certificates | Security team issuance | Network / Security | Airflow UI + dbt docs routes | High | Raise Week 1 — 5 day lead time minimum
PingIdentity OAuth clients | IDP team registration | Network / Security | Airflow auth, Apigee JWT verify | High | Raise Week 1 with environment list
BBH file format spec | BBH team confirmation | BBH Team | BBH transformer image, field mapping | Critical | Kickoff agenda item — confirm Day 1
Node labeling | Cloud engineering | Cloud Engineering | Pod scheduling on new node | Critical | Request in kickoff — 1 day task
Apigee proxy deployment | Apigee team access | Apigee / Integration | CRM → SEI API integration | High | Coordinate with Apigee team Week 1
BBH SFTP connection test | BBH system access | BBH Team | End-to-end file pipeline validation | High | Schedule with BBH team Week 4
UAT sign-off | BBH team participation | BBH Team | Prod go-live | Critical | Schedule UAT window with BBH Week 7-8

## Cloud Eng Scope
Cloud Engineering Scope — Excluded from Your Team Estimate
Task | Description | Est. Days | Impact if Delayed
Provision new OpenShift node | Add 1 node to existing Red Hat OpenShift cluster as agreed | 3 | Blocks all BBH workload scheduling
Label new node for BBH workloads | Apply node labels and taints for BBH pod affinity rules | 1 | Pods schedule on wrong nodes
Cluster admin access grant | Grant OpenShift cluster-admin to data engineering service account | 1 | Blocks namespace and RBAC setup
Image registry enablement | Confirm internal image registry enabled and storage configured | 1 | Blocks all container image builds
StorageClass confirmation | Confirm available StorageClass for PVC provisioning | 1 | Blocks all persistent volume creation
Node monitoring integration | Add new node to existing cluster monitoring (if applicable) | 1 | Gaps in infrastructure health dashboard
⚠ All tasks above are owned by Cloud Engineering. Data Engineering team has zero dependency on performing these — only on their completion.